## Read Me
Instaprotek Portal — Regression Test Tracker
Purpose
A single place to run, track, and report the Instaprotek portal regression suite for each release or hotfix. Use it alongside the Regression Test Plan and the Pre-Release Checklist in this folder.
How to use it
1. Before a run | Duplicate the workbook (e.g. Tracker_v2.4.0.xlsx) so each release keeps its own record.
2. During the run | In the Test Cases tab, work down the suite. Fill the yellow columns: Last Run Date, Status, Actual Result / Notes, Defect ID, Tester.
3. On a failure | Log it in the Defect Log tab, then put its Defect ID back on the failing test case row.
4. To report | The Run Summary tab totals everything automatically — pass rate, defect counts, and a release-readiness flag.
Tabs in this workbook
Test Cases | The regression suite, grouped by portal module. Starter cases — edit, add, and delete to match Instaprotek.
Defect Log | Defects found during testing, with severity, status, and resolution.
Run Summary | Auto-calculated dashboard. Do not type over its formula cells.
Yellow cells = you fill these in
Any column shaded pale yellow is meant to be filled during a run. Everything else is reference content for the suite.
Status values (Test Cases)
Pass | Behaved exactly as the expected result describes.
Fail | Did not match the expected result. Log a defect and add its ID.
Blocked | Could not be run (dependency, environment, or a blocking defect).
Not Run | Not yet executed this cycle (default).
N/A | Not applicable to this release.
Priority values
P1 | Critical — core/blocking. Must pass to ship.
P2 | High — important flow; failures usually block release.
P3 | Medium — should work; assess impact.
P4 | Low — minor / cosmetic.
Example of a filled-in test case row
TC-AUTH-001 | Last Run Date: 2026-07-15 ¦ Status: Pass ¦ Notes: Logged in cleanly on Chrome + Edge ¦ Defect ID: (blank) ¦ Tester: Sarah
Tip: keep one blank master copy of this file and copy it per release so you build a history of regression runs.

## Test Cases
Test ID | Module | Test Case Title | Preconditions | Test Steps | Test Data | Expected Result | Priority | Type | Automated | Last Run Date | Status | Actual Result / Notes | Defect ID | Tester
TC-AUTH-001 | Authentication | Valid login | Active account exists | 1. Open portal login 2. Enter valid username & password 3. Click Log In | standard user | User is authenticated and lands on the dashboard | P1 | Functional | Yes |  | Not Run
TC-AUTH-002 | Authentication | Invalid password rejected | Account exists | 1. Enter valid username 2. Enter wrong password 3. Submit | wrong pw | Error shown; access denied; no session created | P1 | Functional | Yes |  | Not Run
TC-AUTH-003 | Authentication | Password reset flow | Account with valid email | 1. Click Forgot Password 2. Enter email 3. Open reset link 4. Set new password | reset email | Reset email sent; new password works; old one fails | P2 | Functional | No |  | Not Run
TC-AUTH-004 | Authentication | MFA challenge | MFA enabled on account | 1. Log in with valid creds 2. Enter one-time code | OTP code | Access granted only after a valid OTP | P1 | Security | No |  | Not Run
TC-AUTH-005 | Authentication | Account lockout after failed attempts | Lockout policy = 5 | 1. Enter wrong password 5 times | - | Account locked; lockout message shown | P2 | Security | No |  | Not Run
TC-AUTH-006 | Authentication | Session timeout | Logged-in session | 1. Leave session idle past timeout 2. Attempt an action | - | Session expires; user redirected to login | P2 | Security | No |  | Not Run
TC-AUTH-007 | Authentication | Logout ends session | Logged in | 1. Click Log Out 2. Use browser Back | - | Session ended; protected pages inaccessible | P2 | Security | Yes |  | Not Run
TC-USER-001 | User & Role Mgmt | Create new user | Admin logged in | 1. Admin > Users > Add 2. Complete required fields 3. Save | new user | User created, appears in list, can log in | P2 | Functional | No |  | Not Run
TC-USER-002 | User & Role Mgmt | Edit user details | User exists | 1. Open user 2. Edit fields 3. Save | - | Changes saved and persist after reload | P3 | Functional | No |  | Not Run
TC-USER-003 | User & Role Mgmt | Deactivate user | Active user exists | 1. Set user to inactive 2. Attempt login as that user | - | Deactivated user cannot log in | P2 | Functional | No |  | Not Run
TC-ROLE-001 | User & Role Mgmt | Role permissions enforced | Roles configured | 1. Log in as limited role 2. Attempt a restricted action | - | Action blocked; unauthorized message shown | P1 | Security | No |  | Not Run
TC-ROLE-002 | User & Role Mgmt | Admin pages blocked for standard user | Standard user | 1. Navigate directly to an admin URL | /admin | Access denied or redirected | P1 | Security | Yes |  | Not Run
TC-DASH-001 | Dashboard & Nav | Dashboard loads with widgets | Logged in | 1. Load the dashboard | - | All widgets render correct data, no console errors | P2 | Functional | No |  | Not Run
TC-DASH-002 | Dashboard & Nav | Primary navigation links | Logged in | 1. Click each primary nav item | - | Each link routes to the correct page | P3 | Functional | Yes |  | Not Run
TC-DASH-003 | Dashboard & Nav | Breadcrumbs reflect location | Logged in | 1. Navigate through nested pages | - | Breadcrumbs accurate and clickable | P4 | UI | No |  | Not Run
TC-REC-001 | Records / Core | Create record | Create rights | 1. New record 2. Complete required fields 3. Save | sample record | Record created and visible in the list | P1 | Functional | No |  | Not Run
TC-REC-002 | Records / Core | Mandatory field validation | Create form open | 1. Submit with required fields blank | - | Validation errors shown; save blocked | P2 | Functional | Yes |  | Not Run
TC-REC-003 | Records / Core | Edit record | Record exists | 1. Open record 2. Edit 3. Save | - | Updates persist after reload | P2 | Functional | No |  | Not Run
TC-REC-004 | Records / Core | Delete record | Record + delete rights | 1. Delete record 2. Confirm | - | Confirmation prompt; record removed | P2 | Functional | No |  | Not Run
TC-REC-005 | Records / Core | Field-level input validation | Create form | 1. Enter invalid email, date, number formats | bad@, 13/45 | Inline validation errors shown | P3 | Functional | No |  | Not Run
TC-SRCH-001 | Search & Filter | Search returns matches | Records exist | 1. Enter a known term 2. Search | keyword | Relevant results returned | P2 | Functional | No |  | Not Run
TC-SRCH-002 | Search & Filter | Filters narrow results | List has data | 1. Apply one or more filters | status=active | Only matching rows shown | P3 | Functional | No |  | Not Run
TC-SRCH-003 | Search & Filter | Column sort | List has data | 1. Sort ascending then descending | - | Rows reorder correctly | P4 | UI | No |  | Not Run
TC-SRCH-004 | Search & Filter | Pagination | Results exceed page size | 1. Navigate between pages | - | Correct records per page; nav works | P4 | Functional | No |  | Not Run
TC-SRCH-005 | Search & Filter | No-results state | - | 1. Search a term with no matches | zzzzz | Friendly 'no results' message | P4 | UI | No |  | Not Run
TC-DOC-001 | Documents / Upload | Upload valid file | Logged in | 1. Upload an allowed file type | sample.pdf | File uploads and appears in the list | P2 | Functional | No |  | Not Run
TC-DOC-002 | Documents / Upload | Reject invalid file type | - | 1. Attempt to upload a disallowed type | file.exe | Upload rejected with a clear message | P2 | Security | No |  | Not Run
TC-DOC-003 | Documents / Upload | File size limit enforced | - | 1. Upload an oversized file | 60 MB file | Rejected with a size-limit error | P3 | Functional | No |  | Not Run
TC-DOC-004 | Documents / Upload | Download file | File exists | 1. Download an uploaded file | - | File downloads intact and opens | P3 | Functional | No |  | Not Run
TC-NOT-001 | Notifications | Email notification sent | Trigger configured | 1. Perform the action that triggers email | - | Email received with correct content | P3 | Functional | No |  | Not Run
TC-NOT-002 | Notifications | In-app notification | Logged in | 1. Trigger an in-app alert 2. Mark as read | - | Alert appears; mark-as-read works | P4 | Functional | No |  | Not Run
TC-RPT-001 | Reports & Export | Generate report | Data exists | 1. Run a report with parameters | date range | Report renders the correct data | P2 | Functional | No |  | Not Run
TC-RPT-002 | Reports & Export | Export to CSV / PDF | Report available | 1. Export the report | - | File exports, opens, and data matches | P3 | Functional | No |  | Not Run
TC-ACCT-001 | Account & Profile | Update profile | Logged in | 1. Edit profile 2. Save | - | Changes saved and displayed | P3 | Functional | No |  | Not Run
TC-ACCT-002 | Account & Profile | Change password | Logged in | 1. Change password with valid current one | - | New password works; old one fails | P2 | Security | No |  | Not Run
TC-ADM-001 | Admin / Settings | Update system setting | Admin logged in | 1. Change a setting 2. Save | - | Setting applied across the portal | P3 | Functional | No |  | Not Run
TC-ADM-002 | Admin / Settings | Audit log records actions | Admin | 1. Perform an auditable action 2. Check the log | - | Action logged with user and timestamp | P3 | Security | No |  | Not Run
TC-INT-001 | Integrations | SSO login | SSO configured | 1. Log in via the SSO provider | - | Authenticated via SSO with correct profile | P1 | Functional | No |  | Not Run
TC-INT-002 | Integrations | Third-party data sync | Integration active | 1. Trigger a sync | - | Data syncs accurately with no duplicates | P2 | Functional | No |  | Not Run
TC-SEC-001 | Security | Unauthorized direct URL access | Standard user | 1. Access another user's record by ID in the URL | /record/999 | Access denied (IDOR protection) | P1 | Security | No |  | Not Run
TC-SEC-002 | Security | Input sanitization (XSS) | Form available | 1. Enter a script payload in a text field | <script> | Input sanitized; no script executes | P1 | Security | No |  | Not Run
TC-XBR-001 | Cross-browser | Core flows across browsers | - | 1. Run the smoke path in Chrome, Edge, Firefox, Safari | - | Consistent behavior and appearance | P2 | Compatibility | No |  | Not Run
TC-XBR-002 | Cross-browser | Mobile responsive layout | - | 1. Load key pages at mobile width | - | Layout adapts; no broken UI | P3 | UI | No |  | Not Run
TC-PERF-001 | Performance | Key page load time | - | 1. Measure load of dashboard and a large list | - | Loads within the agreed threshold (e.g. < 3s) | P3 | Performance | No |  | Not Run

## Defect Log
Defect ID | Linked Test ID | Summary | Module | Severity | Priority | Status | Steps to Reproduce | Environment | Reported By | Date Reported | Assigned To | Resolution / Notes | Date Resolved
DEF-001 | TC-AUTH-002 | Login screen accepts an expired password once | Authentication | High | P2 | Open | 1. Let a password expire 2. Log in with the old password | Staging | Sarah | 2026-07-15 |  | Under investigation

## Run Summary
Instaprotek Portal — Regression Run Summary
Auto-calculated from the Test Cases and Defect Log tabs. Do not edit these cells.
TEST EXECUTION
Metric | Count | % of total
Total test cases | 44
Passed | 0 | 0%
Failed | 0 | 0%
Blocked | 0 | 0%
Not Run | 44 | 100%
N/A | 0 | 0%
Executed | 0
Pass rate (of executed) | 0%
DEFECTS
Severity | Count
Critical | 0
High | 1
Medium | 0
Low | 0
Total logged | 1
Open (not closed/deferred) | 1
RELEASE READINESS
Status | READY — no failed cases or critical defects
Rule | Ready when Failed = 0 and Critical defects = 0. Adjust to your own gate.